## Sheet1
DATE | Test | Résultats | Comentaire | Errors
OUTDATED APPLICATION
2022-05-01 | Installation | Passed
2022-07-01 | Sign up-sign in | Failed | Unable to sign in -sign up | une erreur inatendue est survenue
2022-10-01 | Password recovery | Failed | Unable to recover password | une erreur inatendue est survenue
On Google Play
19/01/2022 | Password recovery | Passed
19/01/2022 | sign in | Passed
19/01/2022 | Editing profile information | Failed | *City's addresses and Address pannel are not matched(User can insert a random address which is not in the selected city )
*No verification for phone number , so User can verify him/herself with a random phone number
*Mail changing doesn't work( app keeps the old mail)
*Possible to obtain 10 credit by inserting random website
19/01/2022 | publishing Ad panel | failed | * Unable to rotate a vertical picture to a horizontal photo with the same size
* Unable to rotate a horizontal picture to vertical photo with the same size
*Unable to write address for an Ad while a client is able to add 2 Cities
*Unable to add a periode of time ( example: from 19/01/2022 untill 23/01/2022
*Unable to specify minutes for hours ( always 18:00,19:00,20:00)
*Unable to see my Ad which I published
* Credit stays the same after publishing any ad
*There is no lineup of number for uploaded Pictures ,so client needs to remove all the pictures if he/she wants to change the order ot pictures
| adding credits | Passed
old version
21/01/2022 | Installation | Passed
21/01/2022 | Sign up-sign in | Passed
21/01/2022 | Password recovery | Passed
22/01/2022 | Editing profile information | Average | *No need for register client's gender
*Unable to change the email
*for each changes , client needs to reopen 'Compte'
*No verification for phone number , so User can verify him/herself with a random phone number
22/01/2022 | publishing Ad panel | Average | *Unable to write address for an Ad while a client is able to add 2 Cities
*Unable to specify minutes for hours ( always 18:00,19:00,20:00)
*Unable to add a periode of time ( example: from 19/01/2022 untill 23/01/2022
*after publishing an Ad , the textbox stays filled
|  |  | * by tapping on any selected options (date and time , city …) | *Clicked position =0
*There is no lineup of number for uploaded Pictures ,so client needs to remove all the pictures if he/she wants to change the order ot pictures
Adding Credit | publishing Ad panel | Pass | * client can see the price instead of amount in 'Unité'
| Changing password | pass | *by inserting the same old password , it's better to have 'the new password cannot be the same as old password'
Latest Version
26/01/2022 | inscription | passed
| editing profile | passed
Personnal opinion
19/01/2022 | Design | average | Unfinished design = *the enterance of the application shows different pictures for signing in /up
*in personal information , Country's icon and website's icon are the same
*in personal information , 'Site Web' needs to be "Website"
*the placeholder of website must be "Paste your website's URL'
*To add credit , it's better to tap on credit points , instead of tapping on option button
| publishing Ad | average | *80 words limit in not enough
|  |  | * by tapping on any selected options (date and time , city …) | *Clicked position =0